## Slide 1: CLOTT 3 January 24, 2022 Monthly Meeting
“Implementing Best-Practice, Patient-Centered Venous Thromboembolism (VTE) Prevention in Trauma Centers”

## Slide 2: Start Meeting Recording

## Slide 3: Participating Sites
Participating Trauma Centers
University of Maryland
2. Oregon Health & Science University
3. Medical College of Wisconsin
4. Stanford University
5. UC San Diego
6. University of California San Francisco
7. University of Utah
8. Medical University of South Carolina
9. Penn Medicine- Lancaster General Hospital
10. Christiana

## Slide 4: Milestones

## Slide 5: Contracting, IRB, DUA
Site Name | Contract Status | IRB Status | DUA Status
UC San Diego | Executed | Approved | Complete
Lancaster General | Executed | Approved | Complete
University of Maryland | Executed | Approved | Complete
University of California San Francisco | Executed | Approved | Complete
Medical College of Wisconsin | Executed | Approved | Complete
Stanford University | Executed | Approved | Complete
University of Utah | Executed | Approved | In Progress
Medical University of South Carolina | Executed | Approved | Complete
Oregon Health & Science University | Executed | Approved | Complete
Christiana Hospital | Executed | Approved | Complete

## Slide 6: Progress Update: Medication List, Data Submission

## Slide 7: Steps to Building the VTE Prophylaxis Registry and Real Time Alert
Step 1: Medication Identification
Step 2: Review, Validate, and Finalize Medication List
Step 3: Generate 24-month VTE Prophylaxis Registry and Update Every 3 Months
Step 4: Send VTE Prophylaxis Registry to Johns Hopkins
See document: Steps to Building the VTE Prophylaxis Registry and Real Time Alert

## Slide 8: Data Collection Milestones
Data Collection Milestones |  |  |  |  | 
Site Name | Medication List | Initial Data/IT One-on-One Site Meetings | Pull and Review 1 Month of Test Data | Data Contact Provided | Generate Calendar Year 2019 and 2020 Data and Submit to JHU
UC San Diego | Complete | Yes |  | Complete | 
Lancaster General | Complete | Yes | Complete | Complete | 
University of Maryland | Complete | Yes |  | Complete | 
University of California San Francisco | Complete | Yes |  | Complete | 
Medical College of Wisconsin | Complete | Yes |  |  | 
Stanford University | Complete | Yes |  | Complete | 
University of Utah |  | Yes |  | Complete | 
Medical University of South Carolina |  | TBD |  |  | 
Oregon Health & Science University |  | TBD |  | Complete | 
Christiana Hospital | Complete | Yes | Complete |  | 

## Slide 9: Progress Update: Real Time Alert

## Slide 10: Building the Real Time Alert (Complete Excel Sheet)
What communication device does your hospital use to provide real-time notification which can receive the alert when a dose of VTE prophylaxis is missed? (e.g. pager, phone, Epic Secure Chat, etc.)
How will you define your patient population eligible for receiving the patient education bundle? (e.g. floor, service, etc.) The alert will only be triggered for this group.
  Please provide more granular information about floors to be included, patients to be included
Who will receive the alert when a dose of VTE prophylaxis medication is missed and deliver the patient education bundle? (e.g. charge nurse, QI nurse, nurse manager, etc.)
  Do they have access to the device identified in Question 1?
  What is the process to enable the delivery of the education bundle? (e.g. charge nurse mentor the patient's nurse, pharmacist, charge nurse, or resource nurse will deliver education bundle)
  Who will be available to deliver the education bundle 24/7?
  How long after the alert is generated do you expect someone to deliver the intervention?

## Slide 11: Progress Update: Nurse Education Module

## Slide 12: Nurse Education Module (percent complete by site)
Site | Completers | Percent of all Completers | Each Site's Target # | Percent Completed
Penn/Lancaster General | 206 | 25% | 235 | 88%
Stanford University | 109 | 13% | 131 | 83%
University of California San Diego | 127 | 15% | 157 | 81%
University of California San Francisco | 30 | 4% | 450 | 7%
University of Maryland | 40 | 5% | 117 | 34%
University of Utah | 100 | 12% | 141 | 71%
Oregon Health & Science University | 53 | 6% | 60 | 88%
Christiana Hospital | 36 | 4% | 58 | 62%
Medical College of Wisconsin | 9 | 1% | 150 | 6%
Medical University of South Carolina | 5 | 1% | 118 | 4%
Actual Project Total | 715 | -- | 1617 | 44%
Extra Completers (UMD) | 120 | 14% |  | 
All Module Completers | 835 | 100% |  | 
Edited: 1/17/2022 |  |  |  | 

## Slide 13: Progress Update Preparing for Launch: Materials, Peer Coaching

## Slide 14: Implementation Materials: Badge Cards, Posters, Postcards
Customized materials have been sent to your site.
Each site will print materials on their own.
Notes: Customize poster with trauma center logo and policy number

## Slide 15: Patient Education Bundle
Face to face conversation: with a health care provider adjusted to patient learning needs
Patient education handout: developed in collaboration with patients
  Do you have these printed or accessible via device?
Video: 10 minutes featuring clinicians and real VTE patients
  How will you show video?
Notes: A national survey of patients and families who were affected by VTE was done to prioritize topics and delivery methods for educating hospitalized patients about VTE. The results were used to develop this bundle intervention.
This bundle includes

## Slide 16: Peer Coach / Nurse Educator
Dauryne Shaffer RN,MSN,CCRN
  Face to face (limited by distance and travel restrictions)
  Online, live peer coaching
  Preset office hours for support in real time
  Available for team meetings, rollouts, and/or one-on-one reviews

## Slide 17: Manuscript on IRB Process and Challenges

## Slide 18: Manuscript on IRB Experience
Variation in IRB reviews of CLOTT 3 Project
Task: Complete Questionnaire that was emailed on January 6, 2022
This information will provide details such as length of review process time, consent, and challenges.
Plan for peer reviewed publication with CLOTT 3 writing group.

## Slide 19: IRB Information Sheet
IRB Process and Challenges Manuscript | 
Site Name | IRB Information Sheet
UC San Diego | Complete
Lancaster General | 
University of Maryland | Complete
University of California San Francisco | Complete
Medical College of Wisconsin | 
Stanford University | 
University of Utah | 
Medical University of South Carolina | 
Oregon Health & Science University | 
Christiana Hospital | 

## Slide 20: Delphi Survey on Medication Hold of VTE Prophylaxis Doses

## Slide 21: Delphi Study on Peri-Procedural VTE Prophylaxis
Project goals:
  Explore when it is appropriate to hold peri-procedural VTE prophylaxis
    Wide variation in practices and protocols between institutions, physicians, and specialties
  Generate a consensus opinion utilizing the Delphi Method (series of surveys) on when to hold peri-procedural VTE prophylaxis
Notes: Give specific examples.

## Slide 22: Delphi Survey: What to Expect
CLOTT-3 site contacts will receive an email with distribution instructions and survey link in the coming weeks
Site contacts will then distribute initial survey to those providers within specialties of interest
  List will be provided
Subsequent survey will be emailed directly to initial respondents
  Goal: 2-3 responses per specialty per institution
Plan for peer reviewed publication with CLOTT-3 writing group
Notes: PI and main research contact, Highlight importance of distribution (emphasize just first step of the process).

## Slide 23: Announcements

## Slide 24: Register for the 2022 VTE Consensus Conference May 4-5 – Chicago, IL Virtual Attendance Free for Members of CNTR Bit.ly/VTEConference
Bringing together a multi-disciplinary group of stakeholders with expertise in injury care and optimizing VTE prophylaxis in trauma
Promoting research related to delivering timely VTE prophylaxis
Supporting education that improves implementation of current guidelines
Developing research objectives for VTE prophylaxis in trauma

## Slide 25: Apply for Early-Stage Investigator Travel Award for the 2022 VTE Consensus Conference May 4-5 – Chicago, IL
For early career investigators (within 10 years completion of education/training)
Up to $1,500 travel costs
Applications due February 15, 2022
Grab this QR Code to apply

## Slide 26: February 2022 Meeting
Move meeting to
February 28, 2022
Notes: Give specific examples.